## Based on 2023
DEPARTMENT OF AGRICULTURE - REGIONAL FIELD OFFICE III
Annual Procurement Plan for FY 2024
Based on 2023 Continuing Balance
Code (PAP) | Procurement Project | PMO/ End-User | Mode of Procurement | Schedule for Each Procurement Activity |  |  |  | Source of Funds | Estimated Budget (PhP) |  |  | Remarks (brief description of Project)
|  |  |  | Advertisement/Posting of IB/REI | Submission/Opening of Bids | Notice of Award | Contract Signing |  | Total | MOOE | CO
GOODS
Labor and Materials
RICE
RESEARCH
STATION FACILITIES
| Supply of Labor and Materials for the Repair and Rehabilitation of Greenhouse beside the Vegetable Techno-Demo Area 1 at ROS Hillyland (RSHD) Botolan, Zambales | RESEARCH | NP-53.9 - Small Value Procurement | 2024-03-01 | 2024-04-01 | 2024-05-01 | 2024-06-01 | SARO BMB-E-23-0017080 | 408855.11 | 408855.11 |  | for the Repair and Rehabilitation of Greenhouse beside the Vegetable Techno-Demo Area 1 at ROS Hillyland (RSHD) Botolan, Zambales
| Supply of Labor and Materials for the Repair and Rehabilitation of Greenhouse beside the GAP 1 at ROS Lahar Laden (RSLL) San Marcelino, Zambales | RESEARCH | NP-53.9 - Small Value Procurement | 2024-03-01 | 2024-04-01 | 2024-05-01 | 2024-06-01 | SARO BMB-E-23-0017081 | 391144.83 | 391144.83 |  | for the Repair and Rehabilitation of Greenhouse beside the GAP 1 at ROS Lahar Laden (RSLL) San Marcelino, Zambales
| Supply of Labor and Materials for the Repair and Rehabilitation of Plant Nursery in Front of Coffee and Cacao Nursery at ROS Hillyland (RSHD) Botolan, Zambales | RESEARCH | NP-53.9 - Small Value Procurement | 2024-03-01 | 2024-04-01 | 2024-05-01 | 2024-06-01 | SARO BMB-E-23-0017082 | 263077.94 | 263077.94 |  | for the Repair and Rehabilitation of Plant Nursery in Front of Coffee and Cacao Nursery at ROS Hillyland (RSHD) Botolan, Zambales
| Supply of Labor and Materials for the Repair and Rehabilitation of Plant Nursery beside GAP 2 at ROS Lahar Laden (RSLL) San Marcelino, Zambales | RESEARCH | NP-53.9 - Small Value Procurement | 2024-03-01 | 2024-04-01 | 2024-05-01 | 2024-06-01 | SARO BMB-E-23-0017083 | 79712.13 | 79712.13 |  | Labor and Materials for the Repair and Rehabilitation of Plant Nursery beside GAP 2 at ROS Lahar Laden (RSLL) San Marcelino, Zambales
| Supply of Labor and Materials for the Repair and Rehabilitation of Plant Nursery in Front of Equipment Shed at ROS Lahar Laden (RSLL) San Marcelino, Zambales | RESEARCH | NP-53.9 - Small Value Procurement | 2024-03-01 | 2024-04-01 | 2024-05-01 | 2024-06-01 | SARO BMB-E-23-0017084 | 257209.89 | 257209.89 |  | for the Repair and Rehabilitation of Plant Nursery in Front of Equipment Shed at ROS Lahar Laden (RSLL) San Marcelino, Zambales
| Supply of Labor and Materials for the Repair and Rehabilitation of Mushroom Growing House and Storage at ROS Hillyland (RSHD) Botolan, Zambales | RESEARCH | Competitive Bidding | 2024-03-01 | 2024-04-01 | 2024-05-01 | 2024-06-01 | SARO BMB-E-23-0017085 | 1699400 | 1699400 |  | for the Repair and Rehabilitation of Mushroom Growing House and Storage at ROS Hillyland (RSHD) Botolan, Zambales
| Supply of Labor and Materials for the Repair of Vermiculture Facility at ROS Hillyland (RSHD) Botolan, Zambales | RESEARCH | NP-53.9 - Small Value Procurement | 2024-03-01 | 2024-04-01 | 2024-05-01 | 2024-06-01 | SARO BMB-E-23-0017086 | 100000 | 100000 |  | for the Repair of Vermiculture Facility at ROS Hillyland (RSHD) Botolan, Zambales
| Supply of Labor and Materials for the Rehabilitation of Mushroom Tissue Laboratory at ROS Hillyland (RSHD) Botolan, Zambales | RESEARCH | Competitive Bidding | 2024-03-01 | 2024-04-01 | 2024-05-01 | 2024-06-01 | SARO BMB-E-23-0017087 | 1500000 | 1500000 |  | for the Rehabilitation of Mushroom Tissue Laboratory at ROS Hillyland (RSHD) Botolan, Zambales
Agricultural Products
HVCDP
| Red Onion (F1) | HVCDP | Competitive Bidding | 2024-01-01 | 2024-01-01 | 2024-02-01 | 2024-02-01 | HVCDP | 14177835 | 14177835 | 0 | For distribution to the Onion Growers Cooperatives and Associations in the Provinces of Central Luzon affected by Armyworms for the Year 2023-2024
SAAD
Agricultural Supplies
| Corn Husker Sheller | SAAD | NP-53.9 - Small Value Procurement | 2024-01-01 | 2024-01-01 | 2024-02-01 | 2024-02-01 | SAAD | 541000 | 541000 | 0 | To be distributed in the beneficiaries of livelihood project under SAAD Program CY 2024
| Biologics/Livestock | SAAD | NP-53.9 - Small Value Procurement | 2024-01-01 | 2024-01-01 | 2024-02-01 | 2024-02-01 | SAAD | 132000 | 132000 | 0 | To be use for the Livelihood Project under SAAD CY 2024
Office Supplies
| Laptop | SAAD | NP-53.9 - Small Value Procurement | 2024-01-01 | 2024-01-01 | 2024-02-01 | 2024-02-01 | SAAD | 49000 | 49000 | 0 | To be used in SAAD Program for Regional Program Management Office under SAAD CY 2024
ORGANIC
| Provision Services for Organic Third Party Certification of 3 farms | OAP | NP-53.9 - Small Value Procurement | 2024-01-01 | 2024-01-01 | 2024-02-01 | 2024-02-01 | OAP | 390000 | 390000 | 0 | For OA Third Party Certification Assistance of OA Farm s in Region 3
| Multipurpose Shredder Machine | OAP | NP-53.9 - Small Value Procurement | 2024-01-01 | 2024-01-01 | 2024-02-01 | 2024-02-01 | OAP | 623750 | 0 | 623750 | For distribution to OA stakeholders in support to Organic Agriculture Program
| Small Feed Pelletizing Machine | OAP | NP-53.9 - Small Value Procurement | 2024-01-01 | 2024-01-01 | 2024-02-01 | 2024-02-01 | OAP | 201250 | 0 | 201250 | For distribution to OA stakeholders in support to Organic Agriculture Program
| Cassava Grating Machine | OAP | NP-53.9 - Small Value Procurement | 2024-01-01 | 2024-01-01 | 2024-02-01 | 2024-02-01 | OAP | 310767 | 0 | 310767 | For distribution to OA stakeholders in support to Organic Agriculture Program
| Cassava Hydraulic Press Machine | OAP | NP-53.9 - Small Value Procurement | 2024-01-01 | 2024-01-01 | 2024-02-01 | 2024-02-01 | OAP | 227500 | 0 | 227500 | For distribution to OA stakeholders in support to Organic Agriculture Program
| Cassava Washer/Peeler Machine | OAP | NP-53.9 - Small Value Procurement | 2024-01-01 | 2024-01-01 | 2024-02-01 | 2024-02-01 | OAP | 300000 | 0 | 300000 | For distribution to OA stakeholders in support to Organic Agriculture Program
| Pump And Engine (Shallow Tube Well) | OAP | NP-53.9 - Small Value Procurement | 2024-01-01 | 2024-01-01 | 2024-02-01 | 2024-02-01 | OAP | 80000 | 0 | 80000 | For distribution to OA stakeholders in support to Organic Agriculture Program
| Multi-Function Tiller/Cultivator | OAP | NP-53.9 - Small Value Procurement | 2024-01-01 | 2024-01-01 | 2024-02-01 | 2024-02-01 | OAP | 800000 | 0 | 800000 | For distribution to OA stakeholders in support to Organic Agriculture Program
| Multi-Function Tiller/Cultivator | OAP | NP-53.9 - Small Value Procurement | 2024-01-01 | 2024-01-01 | 2024-02-01 | 2024-02-01 | OAP | 640000 | 0 | 640000 | For distribution to OA stakeholders in support to Organic Agriculture Program
| Special High Deep Quality Fryer | OAP | NP-53.9 - Small Value Procurement | 2024-01-01 | 2024-01-01 | 2024-02-01 | 2024-02-01 | OAP | 65000 | 65000 |  | For distribution to OA stakeholders in support to Organic Agriculture Program
| De-Oiler Machine (Basket Spinner Type | OAP | NP-53.9 - Small Value Procurement | 2024-01-01 | 2024-01-01 | 2024-02-01 | 2024-02-01 | OAP | 74000 | 74000 |  | For distribution to OA stakeholders in support to Organic Agriculture Program
| Electric 1Ph foot Pedal impulse Plastic Bag Sealer heat Sealing Machine | OAP | NP-53.9 - Small Value Procurement | 2024-01-01 | 2024-01-01 | 2024-02-01 | 2024-02-01 | OAP | 35000 | 35000 |  | For distribution to OA stakeholders in support to Organic Agriculture Program
| Vacuum Packaging Machine | OAP | NP-53.9 - Small Value Procurement | 2024-01-01 | 2024-01-01 | 2024-02-01 | 2024-02-01 | OAP | 12500 | 12500 |  | For distribution to OA stakeholders in support to Organic Agriculture Program
| Stainless Steel Sink 4 Tub Preparation Table | OAP | NP-53.9 - Small Value Procurement | 2024-01-01 | 2024-01-01 | 2024-02-01 | 2024-02-01 | OAP | 45500 | 45500 |  | For distribution to OA stakeholders in support to Organic Agriculture Program
| Stainless Processing Table | OAP | NP-53.9 - Small Value Procurement | 2024-01-01 | 2024-01-01 | 2024-02-01 | 2024-02-01 | OAP | 117000 | 117000 |  | For distribution to OA stakeholders in support to Organic Agriculture Program
| Heavy duty 16" Impulse sealer | OAP | NP-53.9 - Small Value Procurement | 2024-01-01 | 2024-01-01 | 2024-02-01 | 2024-02-01 | OAP | 3750 | 3750 |  | For distribution to OA stakeholders in support to Organic Agriculture Program
| Digital Weighing Scale | OAP | NP-53.9 - Small Value Procurement | 2024-01-01 | 2024-01-01 | 2024-02-01 | 2024-02-01 | OAP | 2000 | 2000 |  | For distribution to OA stakeholders in support to Organic Agriculture Program
| Manual Scale 20kgs | OAP | NP-53.9 - Small Value Procurement | 2024-01-01 | 2024-01-01 | 2024-02-01 | 2024-02-01 | OAP | 2000 | 2000 |  | For distribution to OA stakeholders in support to Organic Agriculture Program
| Platform scale | OAP | NP-53.9 - Small Value Procurement | 2024-01-01 | 2024-01-01 | 2024-02-01 | 2024-02-01 | OAP | 3500 | 3500 |  | For distribution to OA stakeholders in support to Organic Agriculture Program
| HDPE Plastic Container, Open-Head Drum (220 Liters) | OAP | NP-53.9 - Small Value Procurement | 2024-01-01 | 2024-01-01 | 2024-02-01 | 2024-02-01 | OAP | 35625 | 35625 |  | For distribution to OA stakeholders in support to Organic Agriculture Program
| HDPE Plastic Container, Open-Head Drum (50 -60 liters) | OAP | NP-53.9 - Small Value Procurement | 2024-01-01 | 2024-01-01 | 2024-02-01 | 2024-02-01 | OAP | 45500 | 45500 |  | For distribution to OA stakeholders in support to Organic Agriculture Program
| Industrial Plastic crates with lid | OAP | NP-53.9 - Small Value Procurement | 2024-01-01 | 2024-01-01 | 2024-02-01 | 2024-02-01 | OAP | 12000 | 12000 |  | For distribution to OA stakeholders in support to Organic Agriculture Program
| Stainless Steel basin | OAP | NP-53.9 - Small Value Procurement | 2024-01-01 | 2024-01-01 | 2024-02-01 | 2024-02-01 | OAP | 10000 | 10000 |  | For distribution to OA stakeholders in support to Organic Agriculture Program
| Metal Heavy Duty Steel Storage Rack - 5 tier | OAP | NP-53.9 - Small Value Procurement | 2024-01-01 | 2024-01-01 | 2024-02-01 | 2024-02-01 | OAP | 18750 | 18750 |  | For distribution to OA stakeholders in support to Organic Agriculture Program
SAAD
| Laptop | OAP | NP-53.9 - Small Value Procurement | 2024-01-01 | 2024-01-01 | 2024-02-01 | 2024-02-01 | OAP | 75000 | 0 | 75000 | To be used in OAP Program for Regional Program Management Office under OAP CY 2023
| Desktop | OAP | NP-53.9 - Small Value Procurement | 2024-01-01 | 2024-01-01 | 2024-02-01 | 2024-02-01 | OAP | 225000 | 0 | 225000 | To be used in OAP Program for Regional Program Management Office under OAP CY 2023
| Laptop | OAP | NP-53.9 - Small Value Procurement | 2024-01-01 | 2024-01-01 | 2024-02-01 | 2024-02-01 | OAP | 75000 | 0 | 75000 | To be used in OAP Program for Regional Program Management Office under OAP CY 2023
| Provision Services for Organic Third Party Certification of 3 farms | OAP | NP-53.9 - Small Value Procurement | 2024-01-01 | 2024-01-01 | 2024-02-01 | 2024-02-01 | OAP | 390000 | 390000 | 0 | For OA Third Party Certification Assistance of OA Farm s in Region 3
CONSULTANCY
| GOODS | [7 empty] | #REF! | #REF! | #REF!
| INFRASTRUCTURE | [7 empty] | #REF! | #REF! | #REF!
CONSULTANCY
| TOTAL | [7 empty] | 24419626.9 | 20861359.9 | 3558267
| Consolidated by: |  | Certified Funds Available / Certified Appropriate Funds Available: | [5 empty] | Recommending Approval:
| NORINA L. DAVID, CPA |  | ELIZABETH GRACE N. CANLAS |  |  |  |  | DR. EDUARDO L. LAPUZ, JR.
| Head, BAC Secretariat |  | Budget Officer | [5 empty] | RTD for Operations and Extension/ BAC Chairperson/ BAC Chairperson
Approved:
CRISPULO G. BAUTISTA, JR.
Regional Executive Director

## How-to-fill-out-definitions
| GUIDE TO PREPARE APP | APP COLUMN HEADER/S
STEP 1 | In the Code column, kindly indicate the PAP Code. Please refer to the code indicated in the technical budget posted in the DBM website. For GOCCs and LGUs, indicate the procuring entity's internal numbering system. | Code (PAP)
STEP 2 | For the Procurement Project column, please align descriptions of program/projects with budget documents and ensure clarity and accuracy in describing each procurement program/project. | Procurement Project
STEP 3 | For PMO/End-User, please indicate the PMO/End-User unit who will implement/utilize the procurement program/project. Multiple end-user units are allowed only if the procurement activity was consolidated by the BAC to procure requirements of the end-user units. | PMO/End-User
STEP 4 | For Mode of Procurement and Schedule for Each Procurement Activity, all modes of procurement are available as a dropdown list and requirements for a specific schedule for Ads/Post of IB/REI, Sub/Open of Bids, Notice of Award, and/or Contract Signing are automatically identified thru the MS Excel formula. Note that for Foreign-funded procurement, please use Others - Foreign-funded procurement as the Mode of Procurement. Kindly indicate a specific period (dates, month, quarter) when each Procurement Activity will be done. Please refer to our website: http://www.gppb.gov.ph/timelines/timelines.htm for the specific periods for each activity. Note: For SVP, IB/REI is similar to RFQ. Ads/Post of IB/REI for Shopping 52.1(b) and NP-SVP (53.9) needs to be posted in PhilGEPS for ABCs above 50k. Notice of Award posting in PhilGEPS is mandatory for all Alternative Modes only for ABCs above 50k. | Mode of Procurement | Schedule for Each Procurement Activity
|  |  | Ads/Post of IB/REI | Sub/Open of Bids | Notice of Award | Contract Signing
STEP 5 | For Source of Funds, a dropdown list is available. If the Source of Funds the PE will use is not included, please indicate "Others" and specify under the Remarks column. | Source of Funds
STEP 6 | For Estimated Budget (PhP), kindly fill out either MOOE or CO columns only. Total ABC column is not editable, but will automatically compute for the total MOOE and CO components of the project. This breakdown is needed for tracking purposes. Finally, please ensure that amounts indicated are aligned with budget documents. | Estimated Budget (PhP)
STEP 7 | Before submission to the GPPB, ensure that the Head of the Procuring Entity (HoPE) approves/signs the APP.
GENERAL INFORMATION
#1 | All Cells with Fill Color Orange needs to be filled out by the Agency. This is a visual reminder of blank or improperly filled out cells.
#2 | To ensure that automated indicator which procurement activity needs to be filled out with specific periods, PE must copy entire Excel row with the mode of procurement for the specific procurement program/project and paste on the last sample row "Negotiated Procurement-53.13" in the template.
#3 | If PE wishes to edit formatting and design of borders, fonts, among others of the APP template, it is suggested to utilize the automated formulas in the template before copying contents and reformatting.
#4 | Per Section of 3.1.1 of DBM Circular No. 2015-7, the Approved Budget for the Contract (ABC) shall be “[t]he amount reflected in the MYOA”. Hence, the ABC in the Annual Procurement Plan (APP) shall be the full amount stated in the MYOA with remarks added on how much will be actually disbursed for that particular fiscal year. Moreover, the Procurement Monitoring Report (PMR) should also reflect full amount in the MYOA if the entire contract was awarded within the fiscal year. Thus, for succeeding years, actual disbursements from the MYOA need not be reflected in the APPs and PMRs, unless current contract with MYOA is terminated and a new procurement activity is undertaken.
DEFINITIONS
1. PROGRAM (BESF)– A homogeneous group of activities necessary for the performance of a major purpose for which a government agency is established, for the basic maintenance of the agency’s administrative operations or for the provisions of staff support to the agency’s administrative operations or for the provisions of staff support to the agency’s line functions.
2. PROJECT (BESF)– Special agency undertakings which are to be carried out within a definite time frame and which are intended to result in some pre-determined measure of goods and services.
3. PMO/End User - Unit as proponent of program or project
4. Mode of Procurement - Competitive Bidding and Alternative Methods including: selective bidding, direct contracting, repeat order, shopping, and negotiated procurement.
5. Schedule for Each Procurement Activity - Major procurement activities (advertising/posting; submission and receipt/Opening of bids; award of contract; contract signing).
6. Source of Funds - Whether GoP, Foreign Assisted or Special Purpose Fund
7. Estimated Budget - Agency approved estimate of project/program costs
8. Remarks - brief description of program or project

## data_validation
Competitive Bidding | YES | GoP | 2022 Livestock Program Continuing Balance
Limited Source Bidding | NO | Foreign | 2022 GASS Continuing Balance
Direct Contracting |  | Special Purpose Fund | 2022 4Ks Continuing Balance
Repeat Order |  | Corporate Budget | 2022 OAP Continuing Balance
Shopping |  | Income | 2022 Trust Funds (DA BAR) Continuing Balance
NP-53.1 Two Failed Biddings |  | GAA | 2022 Trust Funds (RAFC) Continuing Balance
NP-53.2 Emergency Cases |  | Others | 2022 Various_MDS Continuing Balance
Emergency Procurement under the Bayanihan Act |  |  | 2022 Trust Funds (PCAF FUND) Continuing Balance
NP-53.3 Take-Over of Contracts |  |  | 2021 Trust Funds (PCAF FUND) Continuing Balance
NP-53.4 Adjacent or Contiguous |  |  | 2022 Balik Probinsya, Bagong Pag-Asa Program (BP2) Continuing Balance
NP-53.5 Agency-to-Agency |  |  | 2022 Rice Program (R&D) Continuing Balance
NP-53.6 Scientific, Scholarly, Artistic Work, Exclusive Technology and Media Services |  |  | 2022 GASS Continuing Balance
NP-53.7 Highly Technical Consultants |  |  | 2022 Rice Program Continuing Balance
NP-53.8 Defense Cooperation Agreement |  |  | 2022 STO AFES Continuing Balance
NP-53.9 - Small Value Procurement |  |  | 2022 FMR Continuing Balance
NP-53.10 Lease of Real Property and Venue |  |  | 2022 Various PSS (Regular) Continuing Balance
NP-53.11 NGO Participation |  |  | 2022 Corn Program Continuing Balance
NP-53.12 Community Participation |  |  | 2022 REGISTRATION, LICENSING AND QUALITY CONTROL Continuing Balance
NP-53.13 UN Agencies, Int'l Organizations or International Financing Institutions
NP-53.14 Direct Retail Purchase of Petroleum Fuel, Oil and Lubricant (POL) Products and Airline Tickets
Others - Foreign-funded procurement